## Sheet1
No. | Description | Tasks
SEP-26 | As any type of user, I want to view Bookeroo's Home Page and Contact Us page so I can take action
Write Ad Copy for the front page
Add registration buttons for both business and regular users
SEP-21 | As any user, I want to be able to add books, so I can sell them.
add a book table in the database
add a book form with name, description, price etc.
upload button saves the book into the database
Create API endpoint for book creation
SEP-10 | As a user, I want to be able to see a preview of a book.
have a preview for every book in plaintext
Book page displays preview text
API endpoint for getting book information
SEP-8 | As a user, I want to be able to search for books by title, author, ISBN, and category
Create ORM for books and implement search logic
Create the frontend UI for searching
Create a search results page
Add API endpoint for searching
SEP-39 | As a user, I want used books and new books of the same kind to be grouped together so I can simplify my search process.
a working search bar
additional query for both used and new condition books
Add API endpoint for searching
SEP-15 | As an unregistered user, I want immediate account registration so I can become a public customer of bookeroo straight away
Add a registration form
Create ORM for users
Create API endpoint for user registration
SEP-16 | As a business I want to register my business on bookeroo pending approval so I can sell and share books on bookeroo (PO clarification for logging in as unverified)
Add registration form
Create ORM for business users
Create API endpoint for business registration
SEP-22 | As a registered user, I want to login to bookeroo, so I can see my dashboard
Create login form
Handle registration session managment
Add API endpoint for authorisation
SEP-17 | As an admin user, I want to approve/suspend users and pending business user registrations so I can do admin things
a working sign up form for business
a list of pending requests for the registered business users
changing the status from pending to approve
Add API endpoint for updating account status